# NexaCare Solutions - Testing and Release Planning Kit

# 1. Test strategy outline

Approach: We will employ a risk-based testing strategy with a focus on functional testing of new features, integration testing for third-party services, performance testing for peak loads, and user acceptance testing (UAT) via a pilot release.

Types of Testing:

Functional Testing: Validate new features (SMS, Calendar Sync, Real-time Availability) meet requirements.

Integration Testing: Ensure seamless communication between NexaCare, the new third-party SMS service, and external calendar APIs (Google, Outlook).

Regression Testing: Verify that existing functionalities (basic clinic scheduling) remain unaffected by version 3.0 updates.

Performance/Load Testing: Simulate 3-5x normal traffic to ensure the system handles Monday 8-10 AM peak booking hours.

Security & Privacy Testing: Ensure 1.2 million patient records are secure and HIPAA compliant during data handling.

Pilot Testing (UAT): Roll out to 20 selected clinics for real-world validation prior to full deployment.

Priorities: Highest priority is given to data integrity (due to past incidents) and performance under peak load, followed by the reliability of the new SMS reminder system.

# 2. Traceability matrix

Req ID | Requirement / Feature | Use Case | Test Case ID | Test Description

:--- | :--- | :--- | :--- | :---

REQ-01 | SMS Reminders | Patient receives SMS 24h & 1h prior | TC-01 | Verify SMS triggers 24h and 1h before appointment.

REQ-02 | SMS Reminders | SMS API handles invalid numbers | TC-02 | Validate error handling when clinic provides an invalid phone number.

REQ-03 | Real-time availability | Clinic updates schedule | TC-03 | Verify schedule changes reflect instantly on patient portal.

REQ-04 | Calendar integration | Sync with Google/Outlook | TC-04 | Verify appointment booking adds event to synced Google/Outlook calendar.

REQ-05 | Redesigned UI | Accessibility & Responsiveness | TC-05 | Validate UI renders correctly on mobile devices and meets accessibility standards.

REQ-06 | Data Security | Secure 1.2M records migration | TC-06 | Verify zero data loss and data integrity post-migration.

REQ-07 | Peak Performance | Monday 8-10 AM traffic | TC-07 | Load test system with 5x concurrent users.

# 3. Annotated test plans

Feature: SMS Reminders Integration

Objective: Verify the third-party SMS service integrates reliably.

Test Steps: Book an appointment; fast-forward system time or check scheduled job; verify SMS receipt.

Risks/Considerations: API rate limits or downtime from the third-party service.

Edge Cases: Invalid numbers, patient opt-out, timezone differences between clinic and patient.

Feature: High-Traffic Performance (Peak Load)

Objective: Ensure platform stability during Monday morning 8-10 AM peak.

Test Steps: Use load testing tools (e.g., JMeter) to simulate 5x normal user logins and booking requests concurrently.

Risks/Considerations: Database deadlocks, application server saturation.

Edge Cases: Sudden spikes beyond 5x due to marketing campaigns or seasonal illnesses.

Feature: Data Migration & Security

Objective: Verify safe transfer of 1.2M patient records.

Test Steps: Perform test migration in a staging environment; run checksums on source and target databases.

Risks/Considerations: Data loss (learning from previous failure), exposed PHI.

Edge Cases: Clinics with missing data fields or legacy API integrations.

# 4. Deployment checklist

Pre-Deployment (Prior to Saturday 12:00 AM)

☐  Notify all 300 clinics of the upcoming maintenance window.

☐  Perform full database and system backup of version 2.x.

☐  Verify rollback environment is provisioned and ready.

☐  Final Go/No-Go meeting with QA, DevOps, Product, and Support teams.

Deployment (Saturday 12:00 AM – 6:00 AM EST)

☐  12:00 AM: Put application in Maintenance Mode.

☐  12:15 AM: Execute data migration scripts to v3.0 schema.

☐  02:00 AM: Deploy v3.0 application code to production servers.

☐  02:30 AM: Run automated post-deployment smoke tests.

☐  03:00 AM: Perform manual sanity checks on core workflows.

☐  04:00 AM: Enable pilot access for the 20 participating clinics.

☐  05:00 AM: Evaluate pilot feedback/logs. Go/No-Go for full release.

☐  05:30 AM: Remove Maintenance Mode; open platform to all clinics.

# 5. Rollback strategy

Conditions for Rollback:

Critical data corruption or data loss detected during migration.

Core booking functionality fails during post-deployment smoke tests.

Unresolvable integration failure with the new SMS API.

Rollback must be initiated by 04:30 AM EST to ensure system restoration before the 6:00 AM window closes.

Rollback Procedures:

1.  Re-enable Maintenance Mode.

2.  Route traffic back to the version 2.x application cluster.

3.  Restore the pre-deployment database snapshot (1.2M records).

4.  Verify data integrity and system stability.

5.  Notify stakeholders of the aborted deployment and rescheduled window.

# 6. Data migration plan

Approach: An Extract, Transform, Load (ETL) approach will be used in a staging environment prior to the live cutover.

Mapping Rules: Map v2.x schema (patient info, appointments) to v3.0, including new fields for SMS opt-in and calendar tokens.

Validation:

Record counts: Ensure exactly 1.2 million records exist post-migration.

Data sampling: Randomly sample records across different clinics to ensure fields (especially sensitive contact info) are correctly populated.

Checksums: Run database checksums pre- and post-migration.

Execution: Conducted during the maintenance window with a full, verified backup taken immediately prior.

# 7. Post-deployment monitoring summary

Metrics to Monitor:

Error Rates: Monitor HTTP 5xx errors and specific API failures (especially the third-party SMS service).

Uptime: Ensure 99.9% availability post-launch.

Latency: Track response times for real-time availability updates and calendar syncs.

System Metrics: CPU, Memory, and Database IOPS on production servers.

Tracking and Reporting Plan:

Use automated monitoring tools (e.g., Datadog, New Relic) with alerts configured for anomaly detection.

Establish a "War Room" for the Support and DevOps teams starting Saturday morning and continuing through the critical Monday 8-10 AM peak period.

Provide a summary report to leadership on Monday at 12:00 PM EST.

# 8. Non-functional requirements and performance plan

Performance Targets:

The system must handle 3-5x normal traffic (Monday peaks) without exceeding a 2-second response time for booking requests.

Real-time availability updates must propagate in under 1 second.

99.9% uptime required during operational hours.

Monitoring Metrics (Golden Signals):

Latency: API response times across the application.

Traffic: Number of concurrent active users and API requests per second.

Errors: Failed booking attempts or SMS API timeouts.

Saturation: Database connection pools and CPU utilization.

Optimization Strategies:

Database Layer: Implement read replicas to offload read-heavy queries (like patients checking availability) from the primary database.

Application Layer: Cache frequently accessed, non-sensitive data (e.g., clinic locations, basic provider info) using Redis.

Infrastructure Layer: Configure auto-scaling groups to automatically provision additional server instances dynamically ahead of the Monday 8-10 AM peak.